## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MC; 02/29; Page (home.ftl) completed and displays correctly. | Pass | MC; 04/01; Buttons work as expected. | Pass | MC; 04/13; Works as expected.
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | MC; 02/29; SignInRoute component completed. | Pass | MC; 04/01; SignInRoute unchanged, unit test added which gets appropriate coverage. | Pass | MC; 04/13; Works as expected.
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Unchanged. | Pass | MC; 04/13; Works as expected.
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Fail | MC; 02/29; Sign in and Username Checking functionality work, however the additional username requirements (minimum one number, etc.) were added at the beginning of Sprint 2. | Pass | MC; 03/02; Username testing completed. | Pass | MC; 04/13; Works as expected.
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; No Comments. | Pass | MC; 04/13; Works as expected.
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Updates to Player Class do not interfere with sign in performance, load time, etc. as predicted | Pass | MC; 04/13; Works as expected.
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Unchanged. | Pass | MC; 04/13; Works as expected.
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MC; 02/28; AcceptGame button initially had "Accept." written, changed to "Accept" removing the period to match "Deny" button. | Pass | MC; 04/01; Buttons work as expected. | Pass | MC; 04/13; Works as expected.
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Works as expected. Route unit tests completed for all start game routes, RequestGame, RequestResponse, and GetGame with appropriate coverage. | Pass | MC; 04/13; Works as expected.
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Works as expected. Route unit tests completed for all start game routes, RequestGame, RequestResponse, and GetGame with appropriate coverage. | Pass | MC; 04/13; Works as expected.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MC; 02/29; No comments. | Pass | MC; 04/01; Works as expected. Route unit tests completed for all start game routes, RequestGame, RequestResponse, and GetGame with appropriate coverage. | Pass | MC; 04/13; Works as expected.
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MC; 02/29; Invalid moves are prevented due to implementation of these states being inomplete. | Pass | MC; 04/01; Move implementation completed, pieces now respond as expected, including forbidding impossible moves. See Move user story for testing info. | Pass | MC; 04/13; Works as expected.
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MC; 02/29; Invalid moves are prevented due to implementation of these states being inomplete. | Pass | MC; 04/01; Move implementation completed, pieces now respond as expected, including forbidding impossible moves. | Pass | MC; 04/13; Works as expected.
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MC; 02/29; Only one move can be made, and with an Ajax call message popping up. The piece can be moved but does nothing as expected. | Pass | MC; 04/01; Move implementation completed, pieces now respond as expected, including forbidding impossible moves. Class move sends information regarding valid moves for client side validation before submitting to server. | Pass | MC; 04/13; Further implementation completed and operational.
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MC; 02/29; Board will need reorienting when updating the board from the server with opponent's move. | Pass | MC; 04/01; Works as expected. Route unit tests completed for all start game routes, RequestGame, RequestResponse, and GetGame with appropriate coverage. Additional BoardView class utilized to ensure correct orientation for both users. | Pass | MC; 04/13; Works as expected.
As a Player I want to be able to click and drag the piece to the move so that I can play the game. | Given it is my turn in the game when I select a piece then I expect to move. |  | N/A | Pass | MC; 04/01; Routing completed for making moves, as well as necessary model components. Only incomplete unit tests are PlayerPiecesTest and RequestResponseRouteTest, which has to be updated. | Pass | MC; 04/13; Works as expected.
| Given that I select a piece when I decide where I want to move then I expect the game to check if it is valid. |  | N/A | Pass | MC; 04/01; Moves are validated and messages for invalid moves work correctly. | Pass | MC; 04/13; Works as expected.
| Given that I have dropped the piece when I am on a valid square then it should be validated. |  | N/A | Pass | MC; 04/01; SubmitTurnRoute and ValidateMoveRoute work as expected. | Pass | MC; 04/13; Works as expected.
| Given that it isn't my turn when an opponent sends a valid move then it should become my turn. |  | N/A | Pass | MC; 04/01; No comments. | Pass | MC; 04/13; Works as expected.
As a Player I want to see which moves are legal when I select a piece so that I do not wast time at impossible moves. | Given it is my turn to move when I select a piece to move then I expect to see the possible places I am able to put the piece down. |  | N/A | Pass | MC; 04/01; Green highlights appear on valid spaces for moves by any player using both SINGLE and KING type pieces. | Pass | MC; 04/13; Works as expected.
As a Player I want to be able to "jump" an opponents piece so that I am closer to winning the game. | Given that it is my turn to move when I select a piece that has the ability to jump then I expect to be able to jump that piece |  | N/A | Pass | MC; 04/02; No comments. | Pass | MC; 04/13; Works as expected.
| Given that I have selected a piece to move when I jump over an opponent's piece then I expect the opponent's piece to be removed from the board. |  | N/A | Pass | MC; 04/02; Required more work than expected to properly update a board with a valid jump move and remove/record pieces jumped. | Pass | MC; 04/13; Works as expected.
| Given that I have selected a piece when I try to make an invalid jump then I expect the game to reject my move and place the piece back to its original spot. |  | N/A | Pass | MC; 04/02; Completed alongside Move user story. | Fail | MC; 04/13; If a piece moves into a position in front of another jumpable piece, the "required jump" message is returned, and a second move must be made to jump the piece.
As a Player I want the ability to jump more than one piece so that I can capture several pieces with a move of several jumps. | Given it is my turn to move when I select a piece then I expect to have the option to jump if possible. |  | N/A | Pass | MC; 04/02; Jump cases are considered in routing, no major notes otherwise. | Fail | MC; 04/13; Required jumps are determined based on the end position of the piece, and so the above error is encountered.
| Given that I have jumped multiple pieces when I am done jumping and there are no more valid jumps within reach then I expect that the pieces that have been jumped are removed from the board. |  | N/A | Fail | MC; 04/02; Completed alongside Move user story. However, some bugs still occur when attempting backwards jumps, seemingly at random. More testing required. | Pass | MC; 04/13; Works as expected.
As a Player I want the ability to "king" my piece when I reach the last row so that I can move my piece in more directions. | Given that I move a piece to the opposite side of the board, its type should be changed to KING before my opponent's turn/my next turn, but only if the move made was valid. |  | N/A | Pass | MC; 04/05; King code inside PostSubmitTurnRoute added in route testing, also added were necessary model component unit tests encompassing all of the King code. Still require assmebly of a designated suite of tests specifically for King code. | Fail | MC; 04/13; A kinged piece may be moved on the same turn it was crowned if the second move is also valid.
| Given that I move a KING piece, I should be able to move it forwards or backwards along the board as valid moves in compliance with the rules for American Checkers. |  | N/A | Pass | MC; 04/04; routes for making moves, validating and submitting moves updated to include specific cases for if a piece to be moved is a King. Unit testing for these cases requires a few additional tests for specific methods. | Pass | MC; 04/13; Works as expected.
As a Player, I want to be able to sign out of the application. | Given that I am signed in when I click "Sign Out," then I should be signed out of the application. |  | N/A |  | N/A | Pass | MC; 04/13; Still require connection to PlayerResignRoute to resign player upon signing out.
| Given I am signed out when I click "Sign Out," then I should be redirected to the home page. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete, player is not resigned from active game when signing out.
| Given that I am in a game when I click "Sign Out," then the game is resigned and I am signed out of the application. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Player, I want to be able to take all of the opponent's pieces so that the game displays a "You Won" screen. | Given the player is making a move, when the player captures the last opponent piece, then that player has won. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given the player has won, when their winning move is sent, the game shows a "You Won" screen. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given a player has one piece left, when their opponent takes their last piece, then that player has lost. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given a player has lost, when the winning move is sent, then the game shows a "You Lost" screen. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given a player wins, when the "You Won" or "You Lost" screen is displayed to the respective users, then the game ends. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given the game has ended, when the players are still on the game screen, then there will appear an option to exit to home. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given there is an exit button, when a player clicks it, the player redirects to the home. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Player, I want to stop my opponent from being able to move so that the game registers me as the winner of the game. | Given I have finished my turn when I stopped the opponent from moving then I expect to win the game. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given that I am the one who lost when I check my turn then I expect a message to say '%player% has captured all pieces.' |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given that I am the one who won the game when I submit my turn then I expect a message to say that 'Congratulations, you have captured all pieces' |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Player I want to be able to resign so that I don’t have to wait for my turn to start. (Resign seen later). | Given I want to end the game when I press the resign button then I expect the game to end. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given the opponent has clicked resign when it is their turn then I expect the game to end when I check my turn. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given the opponent has clicked resign when it is my turn then I expect the game to end when I submit my move. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Spectator I want to be able to select an ongoing game to view it so that I can watch the game unfold. | Given that there is a game going on when I load the home screen then I want to be able to spectate that game. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
| Given I know what game to watch when I click on that game then I want to be redirected to the game page. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Spectator I want to be able to know when the game is over so that I can see who won. | Given the game has ended when I check my turn then I want to be returned to the home page with a description of how the game ended. |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete
As a Spectator I want to be able to stop watching the game in the middle of a match. | Given that I want to stop watching a game when I click the exit button then I expect to be redirected to the home page |  | N/A |  | N/A | Fail | MC; 04/13; Implementation incomplete